## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | • Remove mobile and temporary infrastructure including buildings. • Remove aggregate hardstand areas.
RM2 | Roads and Access Tracks | • Retain for ongoing beneficial use.
RM3 | Remediation of contaminated land | • Contaminated land assessment undertaken by an appropriately qualified person indicates that no contamination unsuitable for the post-mining land use is occurring. If required, a site investigation report including a site suitability statement prepared and submitted in accordance with the provisions of Chapter 7, Part 8 of the EP Act. • Contaminated material either remediated in-situ or removed/transported to an approved landfill for disposal and waste tracking information recorded and submitted.
RM4 | Landform development and reshaping/reprofiling (Native Ecosystem) | Where mine disturbance has occurred, the following apply: • General reshaping and pushing/trimming to achieve final landform with maximum slopes of 26o. • Backfill as required with onsite materials, or clean earth verified in accordance with NEPM guideline values. • Erosion and sediment control systems installed.
RM5 | Landform development and reshaping/reprofiling (Industrial) | • Finalise engineering and design plans. • Batter slopes as per engineered designs or a maximum of 20 - 26 o with a factor of safety of not less than 1.5 which is expected to ensure long term stability. • Backfilling carried out under Level 1 or Level 2 geotechnical supervision and testing in accordance with AS 3798-2007 Guidelines on earthworks for commercial and residential developments (Standards Australia 2007, or most recent edition). • Materials imported for backfilling must be clean earth capable of satisfying the following relevant guidelines: - HIL D – commercial industrial premises of the National Environment Protection (Assessment of Site Contamination) Measure 1999 (amended 2013) - AS 4482.1-2005 - Guide to the sampling and investigation of potentially contaminated soil. Part 1 – Non-volatile and Semi-volatile compounds. - AS 4482.2-2005 - Guide to the sampling and investigation of potentially contaminated soil. Part 2 – Volatile Compounds.
RM6 | Surface preparation | • Remediate any erosion. • Source, cart and spread growth media (topsoil and overburden). • Trim, rock rake and deep rip.
RM7 | Revegetation (Native Ecosystem) | • Assisted natural regeneration supported by demarcation / fencing to exclude access if required. • Where mine disturbance has occurred: - Soil productivity and suitability assessment by an SQP, and gypsum, lime or fertilisers applied where deemed necessary by an SQP. - Supplementary seeding via direct seeding at a rate of 2 kg / ha for tree species and 1 kg/ ha for shrub species where required (TMR 2017). - Minimum 60% strike/survival rate of applied seed mix. • Weeds controlled to reduce competition.
RM8 | Achievement of surface requirements (Native Ecosystem) | • Monitoring to determine whether vegetation is self-sustaining. • Monitoring to determine that species composition is adequate. • Minimum 70% groundcover to be achieved. • No more than 10% groundcover comprised of weed species.
RM9 | Achievement of surface requirements (Industrial) | • Where disturbed land will remain post-surrender subject to ongoing civil works for an industrial end use, Development Permits -Operational Works (or equivalent) in effect. • Where no mine disturbed land remains: - monitoring to determine whether landform is geotechnically safe and stable. - Minimum 70% groundcover to be achieved (through revegetation with grass species, other agreed engineered solution, or combination of both).
RM10 | Achievement of post-mining land use to stable condition (Native Ecosystem) | • Erosion equivalent to, or less than, natural rates for the locality as measured by an SQP. • Species composition consistent with PRCP. • Minimum 70% groundcover to be achieved. • Mortality rate of mature trees equal to, or less than, the recruitment rate of new trees. • No more than 10% groundcover comprised of weed species.
RM11 | Achievement of post-mining land use to stable condition (Industrial) | • Where no mine disturbance is to be transitioned to civil works: - Engineers’ certification that the landform achieves geotechnical stability. - Stormwater management assessment to confirm site is non-polluting. - Contaminated land assessment confirming site is non-polluting. • Where disturbed land will remain post-surrender subject to ongoing civil works for an industrial end use: - Activities consistent with Development Permits - Operational Works (or equivalent).
RM12 | Achievement of post-mining land use to stable condition (Underground ML 4583) | • Assessment by an SQP confirming no subsidence or surface slumping.
RM13 | Achievement of post-mining land use to stable condition (State Road) | • Confirmation that the land is subject to a road reserve / easement (e.g., survey plans).
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1 - Darra
Relevant activities |  |  |  | Mine disturbance areas
Total rehabilitation area size (ha) |  |  |  | 18.725
Commencement of first milestone: RM3 |  |  |  | Commenced
PMLU |  |  |  | Industrial
Date area is available |  |  | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 18.725 | 18.725
Milestone completed by | 2026-12-10 | 2027-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM3 | 18.725
RM5 | 18.725
RM6 | 18.725
RM9 | 18.725
RM11 |  | 18.725
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2 - Darra
Relevant activities |  |  |  | State road reserve
Total rehabilitation area size (ha) |  |  |  | 0.883
Commencement of first milestone: RM13 |  |  |  | Commenced
PMLU |  |  |  | State Road
Date area is available |  |  | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.883
Milestone completed by | 2026-12-10 | 2027-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM3 | 0.883
RM5 | 0.883
RM6 | 0.883
RM9 | 0.883
RM13 |  | 0.883
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3 - Dinmore
Relevant activities |  |  |  | Mine disturbance area.
Total rehabilitation area size (ha) |  |  |  | 47.053
Commencement of first milestone: RM1 |  |  |  | 2161-12-10
PMLU |  |  |  | Industrial
Date area is available | 2161-12-10 | 2162-12-10
Cumulative area available (ha) | 47.053 | 47.053 | 47.053
Milestone completed by | 2162-12-10 | 2167-12-10 | 2168-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 47.053
RM2 | 47.053
RM3 | 47.053
RM5 |  | 47.053
RM6 |  | 47.053
RM9 |  | 47.053
RM11 |  |  | 47.053
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4 - Dinmore
Relevant activities |  |  |  | Buffer / non-mining area
Total rehabilitation area size (ha) |  |  |  | 3.734
Commencement of first milestone: RM1 |  |  |  | 2161-12-10
PMLU |  |  |  | Native Ecosystem
Date area is available | 2161-12-10 | 2162-12-10
Cumulative area available (ha) | 3.734 | 3.734 | 3.734
Milestone completed by | 2162-12-10 | 2165-12-10 | 2168-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 3.734
RM2 | 3.734
RM4 | 3.734
RM6 | 3.734
RM7 | 3.734
RM8 |  | 3.734
RM10 |  |  | 3.734
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5 - Greenwood Village
Relevant activities |  |  |  | Mine disturbance area.
Total rehabilitation area size (ha) |  |  |  | 27.69
Commencement of first milestone: RM1 |  |  |  | 2121-12-10
PMLU |  |  |  | Industrial
Date area is available | 2121-12-10 | 2122-12-10
Cumulative area available (ha) | 27.69 | 27.69 | 27.69
Milestone completed by | 2122-12-10 | 2127-12-10 | 2128-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 27.69
RM2 | 27.69
RM3 | 27.69
RM5 |  | 27.69
RM6 |  | 27.69
RM9 |  | 27.69
RM11 |  |  | 27.69
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6 - Greenwood Village
Relevant activities |  |  |  | Buffer / non-mining area
Total rehabilitation area size (ha) |  |  |  | 3.21
Commencement of first milestone: RM1 |  |  |  | 2121-12-10
PMLU |  |  |  | Native Ecosystem
Date area is available | 2121-12-10 | 2122-12-10
Cumulative area available (ha) | 3.21 | 3.21 | 3.21
Milestone completed by | 2122-12-10 | 2125-12-10 | 2128-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 3.21
RM2 | 3.21
RM4 | 3.21
RM6 | 3.21
RM7 | 3.21
RM8 |  | 3.21
RM10 |  |  | 3.21
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7 - Oxley
Relevant activities |  |  |  | Mine disturbance area
Total rehabilitation area size (ha) |  |  |  | 14.138
Commencement of first milestone: RM1 |  |  |  | 2072-12-10
PMLU |  |  |  | Industrial
Date area is available | 2072-12-10 | 2073-12-10
Cumulative area available (ha) | 14.138 | 14.138 | 14.138
Milestone completed by | 2073-12-10 | 2078-12-10 | 2079-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 14.138
RM2 | 14.138
RM3 | 14.138
RM5 |  | 14.138
RM6 |  | 14.138
RM9 |  | 14.138
RM11 |  |  | 14.138
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8 - Oxley
Relevant activities |  |  |  | Buffer / non-mining area
Total rehabilitation area size (ha) |  |  |  | 0.722
Commencement of first milestone: RM1 |  |  |  | 2072-12-10
PMLU |  |  |  | Native Ecosystem
Date area is available | 2072-12-10 | 2073-12-10
Cumulative area available (ha) | 0.722 | 0.722 | 0.722
Milestone completed by | 2073-12-10 | 2078-12-10 | 2079-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 0.722
RM2 | 0.722
RM3 | 0.722
RM5 |  | 0.722
RM6 |  | 0.722
RM9 |  | 0.722
RM11 |  |  | 0.722
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9 - Redbank Plains
Relevant activities |  |  |  | Mine disturbance area.
Total rehabilitation area size (ha) |  |  |  | 59.0666
Commencement of first milestone: RM1 |  |  |  | 2397-12-10
PMLU |  |  |  | Industrial
Date area is available | 2397-12-10 | 2398-12-10
Cumulative area available (ha) | 59.0666 | 59.0666
Milestone completed by | 2398-12-10 | 2403-12-09 | 2404-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 59.0666
RM2 | 59.0666
RM3 | 59.0666
RM5 |  | 59.0666
RM6 |  | 59.0666
RM9 |  | 59.0666
RM11 |  |  | 57.8366
RM12 |  |  | 1.23
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA10 - Redbank Plains
Relevant activities |  |  |  | Buffer / Non-mining area / surface area of ML 4583
Total rehabilitation area size (ha) |  |  |  | 63.4713
Commencement of first milestone: RM1 |  |  |  | 2397-12-10
PMLU |  |  |  | Native Ecosystem
Date area is available | 2397-12-10 | 2398-12-10
Cumulative area available (ha) | 63.4713 | 63.4713 | 63.4713
Milestone completed by | 2398-12-10 | 2403-12-09 | 2404-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 63.4713
RM2 | 63.4713
RM3 | 63.4713
RM5 |  | 63.4713
RM6 |  | 63.4713
RM9 |  | 63.4713
RM11 |  |  | 63.4713
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).