## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1: Mine infrastructure area
Relevant activities |  |  |  | Mineral processing plant, ore handling facilities and associated infrastructure, workers accommodation village, sewage treatment plant and effluent irrigation infrastructure, solar array and associated infrastructure, water extraction / release infrastructure and airstrip and associated fencing.
Total rehabilitation area size (ha) |  |  |  | 154.5
Commencement of first milestone: RM1 |  |  |  | 2026-06-10
PMLU |  |  |  | Grazing Native Vegetation
Date area is available | 10 Dec Year 26 | 10 Dec Year 30
Cumulative area available (ha) | 134.5 | 154.5
Milestone completed by | 10 Dec Year 30 | 10 Dec Year 35 | 10 Dec Year 40 | 10 Dec Year 44
Milestone Reference | Cumulative area achieved (ha)
RM1 | 134.5 | 154.5
RM2 | 134.5 | 154.5
RM5 | 134.5 | 154.5
RM6 | 134.5 | 154.5
RM7 |  | 134.5 | 154.5
RM8 |  |  | 134.5 | 154.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA2: Retained infrastructure
Relevant activities |  |  | Mine access roads and tracks and Saxby River low level crossing.
Total rehabilitation area size (ha) |  |  | 247.7
Commencement of first milestone: RM10 |  |  | 10 June Year 27
PMLU |  |  | Retained infrastructure
Date area is available | 10 Dec Year 26 | 10 Dec Year 30
Cumulative area available (ha) | 8 | 247.7
Milestone completed by | 10 Dec Year 30 | 10 Dec Year 31
Milestone Reference | Cumulative area achieved (ha)
RM10 | 8 | 247.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3a
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3a: Water Management infrastructure (rehabilitated to light grazing)
Relevant activities |  |  |  | Diversion drains regraded to natural landform and rehabilitated to light grazing.
Total rehabilitation area size (ha) |  |  |  | 52.4
Commencement of first milestone: RM4 |  |  |  | 10 June Year 27
PMLU |  |  |  | Grazing Native Vegetation
Date area is available | 10 Dec Year 26 | 10 Dec Year 30
Cumulative area available (ha) | 39.5 | 52.4
Milestone completed by | 10 Dec Year 30 | 10 Dec Year 35 | 10 Dec Year 40 | 10 Dec Year 44
Milestone Reference | Cumulative area achieved (ha)
RM4 | 39.5 | 52.4
RM5 | 39.5 | 52.4
RM6 | 39.5 | 52.4
RM7 |  | 39.5 | 52.4
RM8 |  |  | 39.5 | 52.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3b
Post-mining land uses (PMLU)
Rehabilitation area |  | RA3b: Water management infrastructure (retained for stock watering)
Relevant activities |  | Raw water dam, sediment dams, pit dewatering dam and process water dam.
Total rehabilitation area size (ha) |  | 69.8
Commencement of first milestone: RM10 |  | 10 June Year 27
PMLU |  | Water storage (on-site stock watering for farm activities)
Date area is available | 10 Dec Year 26
Cumulative area available (ha) | 69.8
Milestone completed by | 10 Dec Year 30
Milestone Reference | Cumulative area achieved (ha)
RM9 | 69.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4: Interim residue storage facility
Relevant activities |  |  |  | Interim residue storage
Total rehabilitation area size (ha) |  |  |  | 1.5
Commencement of first milestone: RM3 |  |  |  | 10 June Year 27
PMLU |  |  |  | Grazing native vegetation
Date area is available | 10 Dec Year 26
Cumulative area available (ha) | 1.5
Milestone completed by | 10 Dec Year 30 | 10 Dec Year 35 | 10 Dec Year 39
Milestone Reference | Cumulative area achieved (ha)
RM3 | 1.5
RM6 |  | 1.5
RM7 |  |  | 1.5
RM8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5: In-pit residue disposal and backfilled pit area
Relevant activities |  |  |  | Residue material placed in-pit and waste rock material placed in the backfilled pit.
Total rehabilitation area size (ha) |  |  |  | 599
Commencement of first milestone: RM4 |  |  |  | 10 June Year 6
PMLU |  |  |  | Grazing native vegetation
Date area is available | 10 Dec Year 5 | 10 Dec Year 10 | 10 Dec Year 15 | 10 Dec Year 20 | 10 Dec Year 25 | 10 Dec Year 30
Cumulative area available (ha) | 17 | 49.8 | 147 | 259.2 | 319.1 | 599
Milestone completed by | 10 Dec Year 10 | 10 Dec Year 15 | 10 Dec Year 20 | 10 Dec Year 25 | 10 Dec Year 30 | 10 Dec Year 35 | 10 Dec Year 40
Milestone Reference | Cumulative area achieved (ha)
RM4 | 17 | 49.8 | 147 | 259.2 | 319.9 | 599
RM5 | 17 | 49.8 | 147 | 259.2 | 319.9 | 599
RM6 | 17 | 49.8 | 147 | 259.2 | 319.9 | 599
RM7 |  | 17 | 49.8 | 147 | 259.2 | 319.9 | 599
RM8 |  |  | 17 | 49.8 | 147 | 259.2 | 599
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6: Out-of-pit waste rock dump
Relevant activities |  |  |  | Out-of-pit waste rock dump.
Total rehabilitation area size (ha) |  |  |  | 39.2
Commencement of first milestone: RM4 |  |  |  | 10 June Year 6
PMLU |  |  |  | Grazing native vegetation
Date area is available | 10 Dec Year 5 | 10 Dec Year 10 | 10 Dec Year 15 | 10 Dec Year 20 | 10 Dec Year 25 | 10 Dec Year 30
Cumulative area available (ha) | 9.4 | 19.6 | 31.3 | 31.5 | 37.7 | 39.2
Milestone completed by | 10 Dec Year 10 | 10 Dec Year 15 | 10 Dec Year 20 | 10 Dec Year 25 | 10 Dec Year 30 | 10 Dec Year 35 | 10 Dec Year 40
Milestone Reference | Cumulative area achieved (ha)
RM4 | 9.4 | 19.6 | 31.3 | 31.5 | 37.7 | 39.2
RM5 | 9.4 | 19.6 | 31.3 | 31.5 | 37.7 | 39.2
RM6 | 9.4 | 19.6 | 31.3 | 31.5 | 37.7 | 39.2
RM7 |  | 9.4 | 19.6 | 31.3 | 31.5 | 37.7
RM8 |  |  | 9.4 | 19.6 | 31.3 | 31.5 | 39.2
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7: Other minor disturbance
Relevant activities |  |  |  | Minor disturbance from other approved disturbance activities resulting in compacted land requiring rehabilitation including topsoil stockpiles on natural surfaces.
Total rehabilitation area size (ha) |  |  |  | 221.2
Commencement of first milestone: RM5 |  |  |  | 10 June Year 27
PMLU |  |  |  | Grazing native vegetation
Date area is available | 10 Dec Year 26 | 10 Dec Year 30 | 10 Dec Year 35
Cumulative area available (ha) | 177.2 | 221.2
Milestone completed by | 10 Dec Year 30 | 10 Dec Year 35 | 10 Dec Year 40 | 10 Dec Year 44
Milestone Reference | Cumulative area achieved (ha)
RM5 | 177.2 | 221.2
RM6 | 177.2 | 221.2
RM7 |  | 177.2 | 221.2
RM8 |  |  | 177.2 | 221.2
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | a) With the exception of any infrastructure to remain as part of the PMLU or where infrastructure is agreed to be retained by the landholder as evidenced by a signed landholder agreement, the following are complete: i. all services disconnected and removed; ii. all concrete, bitumen and gravel roads removed; iii. all operational pipelines drained and removed; iv. all fencing that is not part of PMLU requirements removed; v. all buildings demolished and/or removed off-site; vi. all machinery and equipment removed; vii. all surface water drainage infrastructure removed; and viii. all rubbish removed.
RM2 | Management of contaminated land status | a) Preliminary site investigation completed by AQP1. b) Detailed site investigation report, as required under the Environmental Protection Act 1994, completed. c) Contaminated materials (e.g. PCBs, Dioxins, Mercury, hydrocarbon contaminated soils) removed and appropriately disposed or remediated. d) Validation testing confirms that contaminated soils have been removed or remediated. e) A site suitability statement from a AQP1 confirms the uses or activities for which the land is suitable, align to the approved PMLUs for the site.
RM3 | Removal of waste material | a) Waste within interim residue storage area removed and placed in pit. b) Removal of additional 0.25 m in-situ surface and transferred to pit. c) Soils sampling demonstrates that soils have a: i. soil pH is between pH 5.5 – 9; ii. Low exchangeable sodium potential; and iii. EC suitable for plant growth.
RM4 | Landform development (re-profiling / re shaping) | Landform development works: a) All bulk earthworks and landform reshaping/reprofiling works completed to design specifications. b) Certification provided by an AQP1 confirms that drainage features are constructed to design specifications. c) Geotechnical assessment undertaken by an AQP1 prior to construction confirms that the landform design will achieve long-term stability for each relevant landform. d) Slopes ≤10%. e) Final landforms ≤ 12m above ground level
RM5 | Surface preparation (topdressing, contour ripping, soil amelioration) | a) Prior to each rehabilitation event, soil health and suitability assessed and documented by an AQP1, and a recommendation made for ameliorants to ensure sodicity, salinity, pH and fertility levels are suitable to achieve the relevant PMLU. b) Records of topsoil placement and origin, and evidence indicating achievement of a target depth of 0.2 m (+/- 0.05 m) for all RAs, except for RA5 and RA6 which has a cover of 0.5 m (+/- 0.05 m). c) Records of subsoil placement and origin and evidence indicating achievement of a target depth of 1.5 m. d) Records of any ripping undertaken of minimum depth of 0.3 m. e) Records of ameliorants applied and incorporated into surface, as recommended by an AQP1
RM6 | Achievement of revegetation | a) Seeding of target species in accordance with Table 17: Indicative pasture species seed mix. i) A minimum of four species listed have been seeded.
RM7 | Achievement of low intensity grazing pasture PMLU to stable condition | a) Greater than 60% vegetation cover. b) Native grass species are dominant (>50% cover) in the ground canopy c) No ‘Severe’ erosion4, and drainage follows appropriate paths. d) Weed species presence is ≤15%
RM8 | Achievement PMLU to stable condition | a) Land suitability assessment by an AQP1 certifies that land has achieved a minimum post-mine land suitability3 of Class 4 or 5. b) Soil health assessment confirms soil is suitable for vegetation establishment, and that: i) soil organic matter >0.9 g/100 g); ii) soil pH is between pH 5.5 – 9; and ii) EC is suitable for plant growth. c) Weed cover is ≤10% (excluding exotic pasture grasses). d) Analysis of monitoring data for groundwater, surface water and stream sediments demonstrate that the surrounding environment is statistically equivalent to reference sites (P<0.05). Monitoring is to include dissolved Molybdenum, Strontium and Vanadium. e) Provide a final rehabilitation report including monitoring records.
RM9 | Achievement of stock water storage PMLU to stable and sustainable condition | a) Landholder agreement, transferring ownership and liability of the site agreed and signed by all relevant parties. b) Retained water storage water quality parameters to be below the trigger values for livestock drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZG 2018). c) Concentrations of Molybdenum, Strontium and Vanadium to be statistically equivalent to reference sites / baseline monitoring data (P<0.05). d) All retained water storages assessed as safe and stable by an AQP1. e) Hazard and Safety Assessment completed by an AQP1 demonstrates hazards in RAs are consistent with the type and severity of hazards typical of neighbouring equivalent land use. Remaining hazards are considered to be low risk with no significant increase in risk expected over time.
RM10 | Achievement of retained infrastructure PMLU to a stable condition | a) Hazard and Safety Assessment completed by an AQP1 demonstrates hazards in RAs are consistent with the type and severity of hazards typical of neighbouring equivalent land use. Remaining hazards are considered to be low risk with no significant increase in risk expected over time.
Landholder agreement, transferring ownership and liability of the site agreed and signed by all relevant parties.
1. AQP means a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods, or literature.
2. Department of Science, Information Technology and Innovation and Department of Natural Resources and Mines (2015) Guidelines for Agricultural Land Evaluation in Queensland (Second edition), State of Queensland or later version. https://www.publications.qld.gov.au/dataset/qld-agricultural-land-evaluation-guidelines/resource/d6591386-08e2-453f-a6fa-dff2a756215f.
3. The method for satellite-derived fractional vegetation cover is outlined in Section 3.7.2.4.
4. Erosion classification:
Erosion classification | Minor | Moderate | Severe | Extreme
No. of rill/gully* | <15 | 15–30 | 31–50 | >50
Maximum observed depth (cm) | <10 | 10–30 | 30–60 | >60
*Gully: highly visible form of soil erosion, with steep-sided, incised drainage lines greater than 30 cm deep.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones